## Sheet1
Date | Project Name | Task | Task assigned to | Task Time frame | Remark
2017-04-19 | Mobinsurance Cikitsai Sport psy | Hubspot code email updates configured in Mobinsure live site. | Kiran |  | Informed to client
|  | Citiksai doctors profile modifications done |  |  | updated to client
|  | Sport psy jira issue and request others concept done |  |  | some jira issues cleared, some need to be done
| Folicles | Forgot password for users | Ravali |  | Folicles project ..
In front-end Userdashboard, orders, view profile, edit profile.
| Mobinsurance | Had a call with client and gathered requrements reported to designers and developer. | Sandeep |  | Email sent to client regarding work status Testing is pending.
| Sport psy | Reffred Sport psy jira issues and updated solved issues. |  |  | updated Jira tool.
| Cikitsai | had a chat with client and updated about done modules which is completed and Testing has been done. |  |  | Cikitsai changes done.
| Jai hanuman online market | Done modification according to the client changes. | Rajesh |  | It’s a Wordpress paltform project.